Action Plan-2016-17

NICRA Technology Demonstration Component (TDC)

KVK, Jharsuguda

1.0 A.	Basic information

| S.No. | Item | Detail |
| --- | --- | --- |
| 1.1 | Zone | VII |
| 1.2 | Name of KVK (district) | Jharsuguda |
| 1.3 | Name of Tehsil | Jharsuguda |
| 1.4 | Name of Village | Bhoimunda |
| 1.5 | Climatic vulnerability | Drought/High temperature |

B. Module-wise resilient practice/technology to be demonstrated for the year 2016-17

| Sl.No | Module | Climatic constraint Address | Key Intervention | Measurable indicator (s) |
| --- | --- | --- | --- | --- |
| 1. | Natural Resource Management |  |  |  |
| i | Ridge and furrow method in cow pea | Water stress condition and prolonged dry spell | In-situ moisture conservation and water saving irrigation through ridge and furrow practice in cow pea. | Water use efficiency (Kg/hamm), yield (q/ha), B.C ratio, |
| ii | Ridge & Furrow in Colacassia | Water stress condition and prolonged dry spell | In-situ moisture conservation and water saving irrigation through ridge and furrow practice in Colocassia. | Water use efficiency (Kg/hamm), yield (q/ha), B.C ratio, |
| iii | Mulching in Vegetables | Water stress condition and prolonged dry spell | In-situ moisture conservation through mulching using crop waste, paddy straw and polythene sheet. | Water use efficiency (Kg/hamm), yield (q/ha), B.C ratio, |
| iv. | Low cost poly House | Variable temperature and environment. | Raising of vegetable seedlings in control temperature and climatic condition. | Germination (%), Seedling Survival (%), |
| v. | Low cost net house | Variable temperature and environment. | Raising of vegetable seedlings in control temperature and climatic condition. | Germination (%), Seedling Survival (%), |
| 2. | Crop production |  |  |  |
| i | Drought tolerant paddy var. Sahabhagi dhan | Drought and water stress condition. | Management to drought tolerant in high temperature condition is less, so use of resistant variety increases yield | Water use efficiency (Kg/hamm), yield (q/ha), B.C ratio, |
| ii. | Colocassia cultivation var-Mutakeshi | Drought and water stress condition. | Short duration and water stress resistant colocassia variety-Muktakeshi | Water use efficiency (Kg/hamm), yield (q/ha), B.C ratio, |
| iii. | Cultivation of sweet potato var-Kissan | Drought and water stress condition. | Short duration and water stress resistant Sweet Potato variety-Kissan | Water use efficiency (Kg/hamm), yield (q/ha), B.C ratio, |
| iv. | Crop diversification | Erratic rainfall creates water stress condition in upland | Paddy is replaced by hybrid maize which can be grown in water stress condition getting high income. | Yield (q/ha),Additional income, B.C ratio, |
| v. | Green manuring | Low fertility status of soil due use of chemical inputs. | Incorporation of Dhaincha plant as green manure in paddy before transplanting. | O.C content , Yield,B.C ratio. |
| vi. | Catch crop –Greengram | Low fertility status and less water availability. | Use of residual moisture, growing leguminous crops like-Greengram | O.C content , Yield (q/ha), , B.C ratio, |
| vii. | Intercropping Cauli flower +Marigold | Incidence of pest and disease , | Utilisation of space and moisture with less incidence of pest. | Yield (q/ha),Additional income, % of pest incidence, B.C ratio, |
| viii. | SRI method in Paddy | Less water availability | SRI method paddy cultivation | Water use efficiency (Kg/hamm), yield (q/ha), B.C ratio, |
| ix. | Boron application in Cauliflower. | Low micro nutrient status of soil . | Foliar spray of boron @ 2 gm./ litre at in 15 days interval for 2 times after 30 days and 45 days of planting | Yield (q/ha), B.C ratio, |
| x. | INM in Brinjal | Low fertility status of soil | Azotobacter , Azospirillum and PSB @ 2.5 kg./ ha. Each, soil application of borax 10 kg. per ha. and recommended dose of FYM and NPK. | Yield (q/ha), B.C ratio, |
| xi. | Neem application in Cauli flower | Soil born disease control | Neem cake application in cauliflower | Yield (q/ha), % of disease incidence |
| xii. | Income generation activities. | Low income from crop due to variable climatic condition | Cultivation of paddy straw and oyster mushroom cultivation for income generation. | Yield (q/ha),Additional income, B.C ratio, |
| 3. | Livestock & Fishery |  |  |  |
| i. | Fodder production strategy | Non availability of fodder during cropping season. | Fodder cultivation with Hybrid Napier | Yield (q/ha), B.C ratio, |
| ii. | Feed demonstration | Low nutrient and minerals in normal feed given by farmers. | Feeding of Mineral mixtures blocks to cattle. | Health status, Milching status of cow, additional income. |
| iii. | Feeding with disease management in cattle. | Low mulching capacity and health detoriation due to extreme climate. | Feeding of Mineral mixtures blocks along with health management. | Milching capacity, incidence of disease, additional income. |
| iv. | Low cost poultry house | Increase of mortality due to extreme climatic condition | Low cost poultry house for managing extreme climatic condition. | Mortality %, additional income, body wt., |
| v. | Cementing floor of cattle shed | Prevention from diseases. | Construction of cementing with well drainage system | % of disease incidence. |
| vi. | Backyard poultry | Increase of mortality due to extreme climatic condition | Rearing of improved poultry breed-Banaraja with resistant to extreme climate. | Mortality %, additional income, body wt.,B.C ratio. |
| vii. | Breed up gradation | Less survibility of desi breed to extreme climatic condition. | Rearing of improved breed-Black Bengal with resistant to extreme climate. | Mortality %, additional income, body wt.,B.C ratio. |
| 4. | Community Intervention |  |  |  |
| i. | Vegetable Seed production | Quality seed production | Seed production | -- |

Activities and costs

2.0	Non-recurring contingencies – Equipment

Procurement of farm machinery/ implements for Custom Hiring Centre (CHC)

| S.No. | Item | Unit cost* (Rs) | No. of units | Amount (Rs) |
| --- | --- | --- | --- | --- |
| 1. | Paddy Transplanter | 120000 | 1 | 120000 |
| 2. | Ridger | 80000 | 1 | 80000 |
| 3 | Tractor | 850000 | 1 | 850000 |
|  | Total NRC 2.0 |  | 3 | 1050000 |

* Wherever possible, subsidy extended by State Government for the machinery to be utilized and accordingly rate adjusted. Wherever required, include equipment for village level small weather station, rain gauge and any other critical equipment for community interventions.

3.0	Contingencies

3.1 	Module 1 – NRM interventions

A) 	Repair / Renovation of existing water harvesting structures & drainage channels etc.

| S.No. | Intervention* | Dimensions | No. of benefi-ciaries | Convergence value, if any (Rs) | Value of farmers share, if any(Rs) | Cost to project (Rs) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Drainage channel preparation | 50 m | 20 | -- | -- | 60000 |
| 2. | Bori Check Dam | 3 mx2mx1m | 20 | -- | -- | 20000 |
| 3 | Repair of Tubewell | 2 Nos. | 20 | -- | -- | 20000 |
|  | Sub-total 3.1 |  | 5 |  |  | 100000 |

*de-silting, deepening & clearing of irrigation/drainage channels, repair of defunct wells etc.

B) 	In situ conservation – Resource Conservation Technologies (RCTs)

| Item (specify) | Unit cost Rs/acre | No. of demos | Coverage |  | Amount (Rs) | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Area (acres) | No. of farmers |  |  |
|  | A | B | C | D | A x C |  |
| Ridge & Furrow in Cowpea | 20000 | 10 | 1.0 | 10 | 10000 | Water conservation |
| Ridge & Furrow in Colacassia | 20000 | 10 | 1.0 | 10 | 10000 | Water Conservation |
| Mulching in vegetables | 30000 | 5 | 2.0 | 10 | 40000 | Water conservation, soil conservation ,weed control |
| Low cost poly House | 60000 | 2 | -- | 2 | 120000 | Seedling production |
| Low cost net house | 30000 | 2 | -- | 2 | 60000 | Seedling production |
| Sub-total 3.1 |  | 29 | 4.0 | 34 | 240000 |  |

*Support for improved planting methods, in-situ conservation practices; Specify crops for planting methods and all practices

3.2	Module II – Crop production interventions

A) Stress tolerant / improved varieties.

| Item* | Description |  | Cost (Rs)/acre | No. of demos | Coverage |  | Amount (Rs) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Crop | Variety (s) |  |  | Area (ac) | No. of farmers |  |
|  |  |  | A | B | C | D | A x C |
| Drought | Paddy | Sahabhagi | 2000 | 30 | 15 | 30 | 20000 |
| Flood |  |  |  |  |  |  |  |
| High temperature stress |  |  |  |  |  |  |  |
| Short duration varieties (specify) |  |  |  |  |  |  |  |
| Any other stress (specify, add rows if required) | Colocassia | Muktakeshi | 50000 | 10 | 1 | 10 | 20000 |
|  | Sweet Potato | Kissan | 30000 | 10 | 1 | 10 | 20000 |
| Crop diversification (to other crops) | Maize | 30R77 | 6000 | 20 | 10 | 10 | 30000 |
| Agroforestry |  |  |  |  |  |  |  |
| Seed for green / brown manuring | Dhaincha | -- | 2000 | 10 | 10 | 20 | 10000 |
| Seed for legume catch crops (specify) | Greengram | Tarm-I | 2000 | 5 | 5 | 10 | 5000 |
| Intercropping systems (specify) | Cauli Flower + Marigold | -- | 2000 | 10 | 10 | 10 | 5000 |
| Sub Total 3.2 A |  |  |  | 85 | 47 | 80 | 110000 |

B) Improved agronomic practices and other crop interventions

| Item* |  | Cost (Rs)/ acre | No. of demos | Coverage |  | Amount (Rs) | Remarks (Purpose of intervention) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Area (ac) | No. of farmers |  |  |
|  |  | A | B | C | D | A x C |  |
| Water saving paddy cultivation methods | DSR |  |  |  |  |  |  |
|  | Aerobic |  |  |  |  |  |  |
|  | SRI | 1000 | 5 | 5 | 10 | 5000 | Effective use water and fertilisation |
| Community nursery |  |  |  |  |  |  |  |
| Critical inputs for Integrated crop management (specify crop) |  |  |  |  |  |  |  |
| Critical inputs for Integrated Farming systems (specify inputs and crops) |  |  |  |  |  |  |  |
| Other inputs (soil amendments, soil test based nutrient management, bio-fertilizers, other soil and plant health related etc) |  |  |  |  |  |  |  |
| - Boron Application in Cauli Flower |  | 10000 | 10 | 2 | 10 | 10000 |  |
| - INM in Brinjal |  | 10000 | 10 | 1 | 10 | 5000 |  |
| - Neem application in Cauliflower |  | 10000 | 10 | 1 | 10 | 10000 | Soil born disease reduction |
| Harvesting and post harvesting related interventions |  |  |  |  |  |  |  |
| Facilitating insurance for crops (specify) |  |  |  |  |  |  |  |
| Income generation activities (Mushroom) |  | 40/Bed | 3 | 300 beds | 3 WSHGs | 12000 |  |
| Income generation activities –Vermicomposting |  | 5000/pit | 4 | 4 Nos. | 4 | 20000 |  |
| Facilitation of marketing of farm produce |  |  |  |  |  |  |  |
| Any other (specify), add rows if needed |  |  |  |  |  |  |  |
| Sub-total 3.2 B |  |  | 42 | 9 | 44 & 3 WSHGs | 62000 |  |

4.0 	Module 3 – Livestock & Fisheries interventions

4.1 	Year round fodder production strategies (annual/perennial fodder) in the village

| Season | Name of fodder | Variety | Area (ha) | Unit cost of demo (Rs)* | No. of demos | Amount (Rs)* | Remarks (Purpose of intervention and farmers covered) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Kharif | Hybrid Napier | -- | 0.4 | 2000 | 5 | 10000 | To reduce fodder scarcity problem |
| Rabi |  |  |  |  |  |  |  |
|  | Sub-total 4.1 |  | 0.4 |  | 5 | 10000 |  |

*if applicable

4.2 	Feed demonstrations for crop residue management / stress management: silage / feed blocks/ mineral mixture (MM) blocks / feed enrichment

| Details of feed demo* | Unit cost of demo (Rs) | No. of demos | Amount (Rs) | Remarks (Purpose of intervention and farmers covered) |
| --- | --- | --- | --- | --- |
| - Silage demos |  |  |  |  |
| - Feed block demos |  |  |  |  |
| - Mineral mixture demos | 1500 | 5 | 7500 | 5 |
| - Unconventional feed resources |  |  |  |  |
| - Any other (specify), add rows if needed |  |  |  |  |
| - Feeding management & disease control programme in livestock (Total Mixed Ration, Mineral block, medicines & disinfectant solution) Feed enrichment in cattle | 1500 | 5 | 7500 | 5 |
| Sub-total of 4.2 |  | 10 | 15000 | 10 |

4.3	Improved housing /shelter for protection of livestock against extreme weather

| Type of shelter improvement* | Unit cost of demo (Rs) | No. of demos | Amount (Rs) | Remarks (Purpose of intervention and farmers covered) |
| --- | --- | --- | --- | --- |
| Low cost poultry House | 30000 | 2 | 60000 | 2 Farmer/ SHG |
| Cementing floor of cattle shed | 7500 | 2 | 15000 | To prevent diseases of cattle (2 Nos.) |
| Sub-total of 4.3 |  | 4 | 75000 | 4 Farmers/ SHG |

*Specify animal type and material used; Plan innovative demonstrations using locally available material

4.4	Livestock / Fisheries units

| A | B | C | D | E | F | G |
| --- | --- | --- | --- | --- | --- | --- |
| Enterprise/unit* | Unit cost (Rs) | Convergence share in unit cost, if any** (Rs) | Project share in unit cost (Rs) | No. of units | Cost to Project (D x E) (Rs) | Remarks (Purpose of intervention and farmers covered) |
| Banaraja poultry | 40 | -- | 40 | 500 | 20000 | WSHGs/Farmers |
| Goatery (Black Bengal) | 10000 | -- | 10000 | 1 | 10000 | To upgrade the breed |
| Sub-total of 4.5 |  |  |  |  | 30000 |  |

* Stress tolerant breeds/piggery/goatery/duckery/backyard poultry/ fisheries/bee keeping etc.

5.0 	Module 4 – Community interventions

5.1	Establishment of fodder banks (hay)

| Name of the SHG | Fodder type | Quantity of storage (t) | Unit cost (Rs.) | No. of units | Amount (Rs.) | Remarks (Purpose of intervention and farmers covered) |
| --- | --- | --- | --- | --- | --- | --- |
| Sub-total 5.1 |  |  |  |  |  |  |

5.2 Establishment of Seed banks

| Name of the SHG | Crop and variety | Quantity of storage (t) | Unit cost (Rs.) | No. of units | Amount (Rs.) | Remarks (No. of beneficiaries & Period of use) |
| --- | --- | --- | --- | --- | --- | --- |
| Binapani | Brinjal & Green leaf seed production | 3 kg | 5000 | 5 | 15000 | 5 |
| Binapani | Tomato | 2 Kg | 5000 | 2 | 10000 | 2/ 1 Year |
| Sub-total 5.2 |  | 7 kg |  | 7 | 25000 |  |

6.0.	Capacity Building & Training Programmes

6.1	Training Courses

| Theme | Title of training course | Proposed month | No. of participants | Cost to project (Rs.) |
| --- | --- | --- | --- | --- |
| INM | Soil sample collection technique | May 2016 | 25 | 3750 |
| INM | Nutrient Management in Brinjal | July 2016 | 25 | 3750 |
| INM | Organic Farming | July 2016 | 25 | 3750 |
| IGA | Vermicomposting | July 2016 | 25 | 3750 |
| IGA | Mushroom production technique | July 2016 | 25 | 3750 |
| Production technique | Canopy management of high density plantation | Aug 2016 | 25 | 3750 |
| Production technique | Protected cultivation of Capsicum and Tomato | Aug 2016 | 25 | 3750 |
| INM | Boron application in Cauliflower | September 2016 | 25 | 3750 |
| Sub-total 6.1 |  |  | 200 | 30000 |

6.2	Field Days/ Extension Activities

| Theme | Title of training course | Proposed month | No. of participants | Cost to project (Rs.) |
| --- | --- | --- | --- | --- |
| Soil management | Awareness programme for soil testing and soil test based fertilizer application. | May 2016 | 25 | 3750 |
| Crop Insurance | Awareness campaign on Crop insurance and its benefit. | June 2016 | 25 | 3750 |
| Climate Change | Awareness campaign on climate change & its impact. | June 2016 | 25 | 3750 |
| In-situ conservation | Field day on Green manuring | July 2016 | 50 | 7500 |
| Crop Diversification | Field day on Hybrid Maize | September 2016 | 50 | 7500 |
| Drought Tolerant variety | Field day on Sahabhagidhan | October 2016 | 50 | 7500 |
| Swachha Bharat Mission | Awareness campaign on Swachha Bharat Abhiyan. | October 2016 | 25 | 3750 |
| Nutrient Management | Field day on Boron application in Cauli flower | November 2016 | 50 | 7500 |
| Disease Management | Animal Health Camp (1 No.) | November 2016, December 2016 | 50 | 10000 |
| Poultry Rearing | Field day on backyard poultry | December 2016 | 50 | 7500 |
| Swachha Bharat Mission | Awareness campaign on Swachha Bharat Abhiyan. | January 2017 | 25 | 3750 |
| Organic Farming | Awareness camp on Organic farming | February 2017 | 25 | 3750 |
| Sub-total 6.2 |  |  | 450 | 66250 |

6.3	Exposure Visits

| Place of visit | Purpose of visit | Proposed month | No. of participants | Cost to project (Rs.) |
| --- | --- | --- | --- | --- |
| Koraput | Off season vegetable cultivation | July-December-2016 | 7 | 20000 |
| Berhampur | Improved method of pulse cultivation | Sept- Oct-2016 | 7 | 20000 |
| Sub-total 6.3 |  |  | 14 | 40000 |

7.0	Up-scaling of Successful Interventions

| Sl.No. | Name of technology | Unit cost/ha (Rs.) | No. of farmers covered | Cost to project (Rs.) | Remarks (justification) |
| --- | --- | --- | --- | --- | --- |
| 1. | Disease and pest resistant variety Pratikshya | 5000 | 20 | 10000 | Most adopted variety |
| 2. | Flooriculture-Marigold | 30000 | 5 | 10000 | IGA for WSHGs |
| Sub-total 7.0 |  |  | 25 | 20000 |  |

8.0 Plan for contingency situations involving various crops during the cropping season 2016-17

| Sl. No | Possible contingency situation | Measures envisaged | Unit cost/ acre | No. of farmers to be covered | Cost to project (Rs.) | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Late onset of monsoon | Short duration crops | 10000 | 10 | 10000 | Paddy preference and Pulse alternate |
| 2. | Prolonged breaks during the season | Water saving methods | 10000 | 10 | 10000 | Drip or Sprinkler use |
| 3. | Early withdrawal of monsoon | Moisture stress crop planning | 10000 | 10 | 10000 | Cow pea, Short duration paddy |
| 4. | Intense storms | -- | -- | -- | -- | -- |
| 5. | Temporary flooding/ Water logging due to heavy rains | Drainage system development | 10000 | 10 | 10000 | Drainage clearance machine. |
| 6. | Any other, .. |  |  |  |  |  |
| Sub-total 8.0 |  |  |  | 40 | 40000 |  |

9.0	Contractual Manpower (SRFs)

| Category | Rate/month (Rs.) | No. of positions | No. of months | Amount (Rs.) |
| --- | --- | --- | --- | --- |
| SRF-1 | 28000 | 1 | 12 | 306000 |
| SRF-2 | 28000 | 1 | 12 | 306000 |
| Sub-total 8.0 |  |  |  | 612000 |

10.0	Media Products to be developed (brochure/bulletin)

| Item description | No. of copies | Amount (Rs.) |
| --- | --- | --- |
| News Letter (2 Nos. @ Rs.6500) | 500 each | 13000 |
| Booklets (3 Nos.@Rs.6500) | 500 each | 19500 |
| Video/CD making (5 Activities @Rs.4000/-) | 5 | 20000 |
| Sub-total 9.0 |  | 52500 |

Summary of budget Estimates for 2016-17 (Tentative)

| Sub total | Item | Amount (Rs) |
| --- | --- | --- |
| 2.0 | Procurement of farm machinery/implements for CHC | 1050000 |
| 3.1. A | Repair/ Renovation of existing water harvesting structures & drainage channels etc. | 100000 |
| 3.1. B | In situ conservation – Resource Conservation Technologies (RCTs) | 240000 |
| 3.2. A | Stress tolerant/ Improved varieties | 110000 |
| 3.2. B | Improved agronomic practices and other crop interventions | 62000 |
| 4.1 | Year round fodder production strategies (annual/perennial fodder) in the village | 10000 |
| 4.2 | Feed demonstrations for crop residue management / stress management: silage / feed blocks/ mineral mixture blocks / feed enrichment | 15000 |
| 4.3 | Improved housing /shelter for protection against extreme weather | 75000 |
| 4.4 | Livestock/fisheries units | 30000 |
| 5.1 | Establishment of fodder banks (hay) | -- |
| 5.2 | Establishment of seed banks | 25000 |
| 6.1 | Training courses | 30000 |
| 6.2 | Field days | 62250 |
| 6.3 | Exposure visits | 40000 |
| 7.0 | Up-scaling of successful interventions | 20000 |
| 8.0 | Plan for contingency measures for various crops during the cropping season 2016-17 | 40000 |
| 9.0 | Contractual manpower (SRFs) | 612000 |
| 10.0 | Media products to be developed | 52500 |
| 11.0 | Any other contingencies (TA etc) | 150000 |
|  | Grand total | 2723750 |

Date:                                                        	 Signature of PC, KVK/ In-charge NICRA

Date:	                                         	Signature of Nodal Officer, NICRA-ZPD Zone-VII